## How To Use
How to Use
Purpose
Records the checks performed before, during and after a production deployment, and the final result. It confirms the change was tested, peer reviewed and approved before go-live, with a rollback plan in place. Attach the completed checklist to the change ticket.
When
Starts | Peer review (EDI-TPL-02) is Approved and the change window is scheduled.
Ends | Every Closure check is Yes, and Deployment Result and Closure Date are filled in on the Overview tab.
Who | The deployer, who also validates the change in production and closes the ticket.
Steps
1. | Complete the Change Details and Rollback Plan on the Overview tab before the change window opens.
2. | Work through the Deployment Checklist tab in order. For each check, set Result to Yes, No or N/A and add Notes where needed.
3. | Do not start the Deployment phase until every Pre-deployment check is Yes or N/A.
4. | If a rollback trigger occurs, restore the rollback version, notify the partner contact, and follow the reprocessing approach on the Overview tab.
5. | Record the Actual Deployment Datetime and Final Map Version (PROD) on the Overview tab, then complete the Closure checks.
6. | Set Deployment Result to Successful, Rolled Back or Completed with Issues, then enter the Closure Date.
Notes
• Use N/A only for "where required" or "where applicable" checks that do not apply (for example DC-06 integration testing for a configuration-only change), and give the reason in Notes.
• A brand-new map has no production version. Record "None – new map" as the Rollback Version and mark DC-11 and DC-15 N/A.
• Checklist Status updates automatically. A Deployment Result of Successful turns red if any check is No or unanswered.
• Completed with Issues means the change is live but something is outstanding. Describe it in Notes on the affected check and record the follow-up CR ID.
• Record datetimes in 24-hour format (e.g. 2026-10-06 21:45) in the change window's time zone.
• Portfolio sample. All entities and data are fictional.
Why the rollback plan comes first
A rollback plan written during an incident is a guess made under pressure. Agreeing the version, trigger, reprocessing approach and partner contact before the window opens turns a failed deployment into a routine, reversible step.

## Overview
Overview
Change Details
Change / Ticket ID
Map Name
Map Version
Target Implementation Datetime
Assigned To
Approved By
Rollback Plan
Rollback Version (current production)
Rollback Trigger | Rejected transactions, data corruption, or business-blocking error
Reprocessing Approach
Deployment Outcome
Checklist Status (automatic) | 33 check(s) not answered
Actual Deployment Datetime
Final Map Version (PROD)
Deployment Result
Deployed By
Closure Date

## Deployment Checklist
Deployment Checklist
ID | Item to Check | Result | Notes
A. Pre-deployment
DC-01 | Change request approved (Approved By recorded on the Overview tab)
DC-02 | Deployment window confirmed
DC-03 | Required stakeholders notified, including the partner if the change affects them
DC-04 | Business sign-off recorded; partner sign-off too if required.
DC-05 | Unit testing passed (EDI-TPL-01)
DC-06 | Integration testing passed where required (EDI-TPL-01)
DC-07 | Regression testing passed where required (EDI-TPL-01)
DC-08 | Peer review (EDI-TPL-02) completed and approved, critical findings closed
DC-09 | Correct deployment artifact identified
DC-10 | Production map/version verified
DC-11 | Backup or previous version available
DC-12 | Dependencies confirmed (code lists, business processes, envelopes)
DC-13 | Rollback procedure reviewed (Rollback Plan on the Overview tab)
B. Deployment
DC-14 | Correct production environment confirmed
DC-15 | Current production map/version backed up
DC-16 | New map deployed
DC-17 | Compilation/validation successful
DC-18 | Correct version activated
DC-19 | Associated configuration deployed where required (trading partner relationship, routing, code lists)
DC-20 | No deployment errors observed
C. Post-deployment
DC-21 | Production validation executed; first production transaction processed end to end
DC-22 | Expected output confirmed
DC-23 | Routing confirmed
DC-24 | Acknowledgment/response received and reconciled where applicable
DC-25 | Monitoring/logs reviewed
DC-26 | No unexpected errors detected
DC-27 | Business/requestor notified where required
DC-28 | Hypercare owner and end date assigned
D. Closure
DC-29 | Deployment evidence attached (EDI-TPL-01, EDI-TPL-02 and this checklist)
DC-30 | Final version recorded (Final Map Version (PROD) on the Overview tab)
DC-31 | Production validation documented
DC-32 | Change record updated
DC-33 | Change closed

## Lists (hidden)
Result | Deployment Result
Yes | Successful
No | Rolled Back
N/A | Completed with Issues